# Design for a New Qualitative Evaluation Study of Escola Ativa

This will be a study of the complex changes being made in teaching and learning in EA program, rural-area schools with multi-grade classrooms in poor sections of the Midwest, North and Northeast.  Close attention will be made to child development, pedagogy, curriculum, school organization, and community relations, all within a framework of regional and state educational policy. The field work will be carried out with school names and personnel anonymized.

| Studies | Focus of the studies | Products | Timeline |
| --- | --- | --- | --- |
| 1. CASE STUDIES | The first focus of the study will be via intensive observations to be made at a small number of schools, probably one in each of the three regions, by experienced educational field researchers. In addition to observing school activities for at least three weeks, and related community and professional development activities, the researcher will interview the teacher, the supervisor, children, parents and community members. | For each of three case researchers - Monthly progress report (1 page) indicating problems encountered, changes in plan. - Field Notes sent to the Documentarian (electronic files photocopies of documents) - Stories sent to the Oral Historian (elelctronic files, photocopies of documents) - Case Study: Rought draft - 30 pages - Administrative summary of work completed - Case Study: Final draft - 30pages | Data Collection - Dec 31/2001 Mini-case-Observing and writing a two-page mini-report on school visit- September/2001 Administrative summary of work completed - December 31/2001 Rough Draft - December 31 /2001 Final Drafts - January 31/2002 |
| 2- ORAL HISTORIES | The second focus of the study will be via gathering brief oral histories of teacher and student, and other persons experienced with the EA program, including opportunities and problems, gathered with regard to a set of issue questions but growing throughout the study. The oral histories will be gathered in depth and detail by the oral historian in one school and with more framing and screening in a number of mini-case study schools, (Indicated below to be perhaps one in each of three states in each region, for a total of ten schools in addition to the three full cases mentioned earlier . | - Monthly progress report, indicating problems encountered and changes in plan. - Field Notes sent to the Documentarian (electronic files + copy of other documents) - Stories sent to Oral Historian (elelctronic files, photocopies of documents) - Mini Case Study: Rought draft - Administrative summary of work completed - Draft report on the Analysis of the Oral Histories - Final Draft of the Oral Histories | Data Collection - Dec 31/2001 Mini-case-Observing and writing a two-page mini-report on school visit- September/2001 Administrative summary of work completed - December 31/2001 Rough Draft - December 31 /2001 Final Drafts - January 31/2002 |
| 3. DISCIPLINE-BASED ANALYSIS ON EA PROGRAM: Child development Pedagogy and Curriculum School and Community National and Regional Policy | The third focus of the study will be a discipline-based commentary on the EA program by four recognized writers, each providing a contextualized critique of the case materials and oral histories gathered by the team but adding their own observations and readings as well. We intend to have a child development specialist write about the intellectual and social maturation of the children of these communities participating in the EA work. We intend to have a teacher specialist, probably a teacher educator, writing about EA activities as they relate to theories and practices of pedagogy and curricula. We would like to find a sociologist particular interested in rural development who would see the schools and communities struggling these impoverished areas. And we would like an educational policy studies specialist look at federal and regional policies as they relate to the development of an Escola Ativa ethic. | Products from each of four topical writers - Monthly progress report, indicating problems encountered and changes in plan. - Field notes sent to the Documentarian (electronic files + copy of other documents) - Mini Case Study: Rought draft - Chapter Draft report - Administrative summary of work completed - Final draft of topical chapter | Data Collection - Dec 31/2001 Mini-case-Observing and writing a two-page mini-report on school visit- September/2001 Administrative summary of work completed - December 31/2001 Rough Draft - December 31 /2001 Final Drafts - January 31/2002 |
| 4. MINI-CASE STUDIES | The Associate director, the Oral historian, the Topic-Writers, the field workers and the Documentarian, will conduct mini-case studies. These studies will be one to two-day site observation. There will be about 10-15 mini-cases. They are mentioned in the duties and products above. | They are mentioned in products above. | Mini-case-Observing and writing a two-page mini-report on school visit- September/2001 |
| 5. PRODUCTS FROM THE DIRECTOR DISSEMINATION | A final report will be prepared in 6"x9" perfect bound book fashion with cover and 200 copies provided for distribution. The expected length of the book will be 300 pages. No photographs but possibly some drawings. Table of contents for 11 chapters | - Guidelines for selecting schools, collecting and analyzing case study data. - Monthly status report - Final Report of the study Chapters of the final Report - The EA Program and the evaluation design - School Case #1 - School Case #2 - School Case #3 - Other Schools - Oral history - Child Development - Pedagogy and Curriculum - School and Community - National and Regional Educational Policy - Evaluation Summary | Final Report - April /2002 |
| GRAND TOTAL: US$ 184,728 |  |  |  |

Proposed by Dr. Robert Stake, Director of the Center for Instructional Research and Curriculum Evaluation, University of Illinois, IL, USA