Illustrative Proposal for a Large Sized Evaluation Study

### Proposal for a Qualitative Evaluation Study

of Fundascola's Escola Ativa Program (EA)

Robert E. Stake, University of Illinois

This is a proposal to study the quality of the educational activities of the Escola Ativa program, including teaching, learning, professional development, community support, and state and federal management.

The evaluation work is to begin in mid-August,  to complete the fieldwork and data gathering by December 31, and to have a report available for distribution by April 1, the following year.

This will be a study of the complex changes being made in teaching and learning in EA program, rural-area schools with multi-grade classrooms in poor sections of the Midwest, North and Northeast.  Close attention will be made to child development, pedagogy, curriculum, school organization, community relations, all within a framework of regional and state educational policy.

PROGRAM

Escola Ativa is understood to be a pedagogical strategy combined with contemporary school management ideas.  Based on twenty years of successful development in Columbia, the strategy aims at improved curriculum, instruction and student learning.

The following elements are important to the plan:

- Professional development for teachers on the EA strategy, with participating teachers receiving in-service training on methodology and follow-up support from supervisors and micro-centers.

- Distribution of textbooks specially designed for multi-grade classrooms to all students and pedagogical kits to the teachers.

- Each child proceeding at his or her own pace.

- Each classroom having a number of learning centers.

- Students involved in the management of the school and the learning activities, and members of the community also involved.

- Cooperative learning emphasized.

- Continuous evaluation of student work to track individual progress.

Some schools have completed their three years of support from Fundescola.  Some 1400 are currently being supported and more are scheduled in the future.  These schools are located in 19 states with special assistance from the State and Municipal School Office.

This qualitative study will accompany a quantitative large-scale sampling study currently being contracted with support from the World Bank.  Some of the quantitative findings would be valuable in understanding the qualitative findings projected here but the qualitative study will be done much sooner.  It is hoped that it will provide insight into the educational processes locally and nationally for enhancing interpretation of quantitative findings.

EVALUATION ISSUES

This is a starter list of etic issues, to be supplemented  from team planning and with issues identified by the organizers and teachers of Escola Ativa.

1.   Does Escola Ativa attain active engagement in learning?

- Does Escola Ativa cause children, teachers, and parents to be advocates for experiential primary education?

- Is basic skill learning under-emphasized and under-accomplished?

- What types of assessment best represent the performance of EA students, consistent with the goals and format of the program?

- What can be recommended as to how EA schools should be included in the federal accountability system?

- Does Escola Ativa incline parents to leave children in school longer?

- Do EA supervisors effectively help teachers solve instructional problems?

- How are student performances evaluated and acknowledged ready for promotion?

- In what ways are students identified as belonging to a grade level?

- Do the demand for appropriate instructional publications exceed the supply?

- Do EA teachers let and help students teach each other?

- Do forthcoming standardized tests pose a threat to EA teachers and students?

- How are Mayors and community leaders treating the Escola Ativa schools?

- What are the ideological values sustaining and emerging in EA schools?

- What is the school doing to maintain the educational approach after EA funding ends

- In what ways are and are not Fundescola professional development activities appropriate for supervisors?

Special foci of attention for the Topical Writer on Child Development:

CD1.What is happening to these children as they take responsibility for schools spaces and activities?

CD2.What is happening to the expectation that the children will need to leave school for providing assistance to the family?

CD3. Is the strategy of putting children in charge of certain school spaces and activities contributing to their social development without trivializing instruction and diminishing the teacher's capability and authority?

CD4.Do the children's responsibilities extend to conflict resolution and subduing violence?

CD5. Is the mixture of children of different ages, some of them as old as twelve, compromising the efforts of the EA curriculum to teach basic skills via group learning?

Special foci of attention for the Topical Writer on Pedagogy and Curriculum:

PC1.  How have teachers in Escola Ativa schools changed teaching philosophy and practice?

PC2. Are the skills of reading, writing, and oral expression getting adequate priority?

PC3. Is the Escola Ativa effort to teach reading and writing via whole language approach more effective than using the syllabic approach?

PC4. Are the EA teachers able to apply the whole language approach with no more than a few days professional development?

PC5. What is the quality of the special instructional materials provided EA schools?

PC6. Is the Pró-Formação program assisting teachers toward a teaching certificate compatible with the Escola Ativa rationale?

PC7. What is the strategy of Fundescola for professional development of supervisors and is it consistent with the aims of Escola Ativa?

PC8. What happens to children who have spent four years in the child-centered EA schools and then go to a traditional Grade 5 class?

Special foci of attention for the Topical Writer on School and Community:

SC1. What could be done to make the federal accountability assessment easier for EA schools to participate in and effectively represent what they are doing?

SC2.What are community sources of support for the EA schools?

SC3.What happens when an outgoing Mayor has identified closely with the EA school?

SC4.After three years of funding ends, what are the factors determining whether or not the EA educational approach is maintained?

SC5.Does Escola Ativa create a need for additional Grade 5 classes?

Special foci of attention for the Topical Writer on State and National Affairs:

SN1.How does the State and Municipal Secretary of Education influence the EA program?

SN2.With accountability initiatives, especially using standardized curricula and testing, prominent in most countries around the world, how is this program politically viable?

SN3.What is Fundescola's policy for transition of children from EA schools to traditional schools?

SN4.Will Escola Ativa extend the number of years small communities need to provide schooling?

EVALUATION DESIGN

The first focus of the study will be via intensive observations to be made at a small number of schools, probably one in each of the three regions, by experienced educational field researchers.  In addition to observing school activities for at least three weeks, and related community and professional development activities, the researcher will interview the teacher, the supervisor, children, parents and community members. There will also be about 10-15 mini-case studies, one to two-day site observation. The Associate director, the Oral historian, the Topic-Writers, the Case Study Researchers and the Documentarian will conduct the mini-cases.

The second focus of the study will be via gathering brief oral histories of teacher and student and other persons experienced with the EA program, including opportunities and problems, gathered with regard to a set of issue questions started above but growing throughout the study. The oral histories will be gathered in depth and detail by the oral historian in one school and with more framing and screening in a number of mini-case study schools, to be perhaps one in each of three states in each region, for a total of ten schools in addition to the three full cases mentioned earlier.

The third focus of the study will be a discipline-based commentary on the EA program by four recognized writers, each providing a contextualized critique of the case materials and oral histories gathered by the team but adding their own observations and readings as well.  We intend to have a child development specialist write about the intellectual and social maturation of the children of these communities participating in the EA work.  We intend to have a teacher specialist, probably a teacher educator, writing about EA activities as they relate to theories and practices of pedagogy and curricula.  We would like to find a sociologist particular interested in rural development who would see the schools and communities struggling these impoverished areas.  And we would like an educational policy studies specialist look at federal and regional policies as they relate to the development of an Escola Ativa ethic.

PERSONNEL RESPONSIBILITIES.

The Director, an experienced educational research manager familiar with qualitative research methods, will have administrative responsibility for the study including selecting or endorsing team personnel, negotiating the contract and statements of work, making fiscal arrangements including an accounting system, making arrangements with appropriate officials in the Ministry and in the State offices of education, working with the Associate Director in selecting sites and training routines, working out reporting and filing systems with the Documentarian as well as approving his/her plan for the final report, and generally overseeing the progress of the study.

The Associate Director, a researcher experienced in educational fieldwork, will be the conceptual coordinator of the study and the supervisor of field operations.  He/she will prepare information for the selection of sites and field workers, choose the sites and field workers with the Director, prepare the supervisors to be helpful to the study, prepare the field workers for their work, assist the fieldworkers in arrangements with their sites and supervisors, back them up in their data gathering, discuss with them the development of their stories, providing model writings, read drafts and assist with member checks.  For the issue development commentaries, he/she will work with the four topical writers, helping them to be acquainted with the field operations and to use field data in their interpretation and writings.

The Oral Historian, probably an anthropologist, will outline an issues-based and procedural plan for inviting oral histories and vignettes and commentaries from all EA teachers who wish to volunteer them, and categorize them and prepare them for review by the Topical Writers.  He/she will be the team visitor to a small selection of schools, observing and interviewing for preparation of a two page mini case report for each of them, plus seeking out stories and quotations for the oral history collection.  From the entries, preferably from those that the Topical Writers do not wish to use in their chapters, the Oral Historian will prepare a 15,000-word chapter on Oral Histories.

The Documentarian, an experienced writer, probably as co-author with the director and associate director, will manage the preparation of the 150,000 word report, and will author the introductory and final interpretation sections, each of perhaps 15,000 words.  He/she will assure the thematic integrity of the report and will choose its format, the rules for submitting drafts, and deadlines.  He/she will provide editorial assistance for all writers.

Each of the three Field Workers will spend at least fifteen days at or near the school, observing school and community activities, getting acquainted with the teacher, the EA supervisor, the Mayor or his/her educational resource person, the students and a few parents.  He/she will interview key people, maintain topical contact through the Documentarian with the progress of the Topical Writers, and prepare a 15,000-word section of the final report.

There will be a Topical Writer-Interpreter for the following topics, probably with the indicated expertise:  Child Development (child development expert), Pedagogy and Curriculum (a teacher educator), School and Community Life, (a sociologist) and Regional and National Affairs, (a polidy studies person or political scientist).  These essayists will begin work as the site visitors are closing their work, visiting a school themselves for preparation of a 1000 word mini-report, reading draft materials from the field workers and stories provided by the Oral Historian.  Their section of the final report will be a commentary on the relationships of the Escola Ativa program and pertinent aspects of their special fields.

REPORTS.  The field work will be carried out with school names and personnel anonymized.

A final report will be prepared in 6"x9" perfect bound book fashion with cover and 250 copies provided for distribution.  The expected length of the book will be 300 pages.  No photographs but possibly some drawings.  Table of contents for 11 chapters

The EA Program and the evaluation design

School Case #1

School Case #2

School Case #3

Other Schools

Oral history

Child Development

Pedagogy and Curriculum

School and Community

National and Regional Educational Policy

Evaluation Summary

A brief monthly progress will be submitted to the host institution and to Fundescola, indicating problems encountered and changes in plan.

First Focus: Full Case Studies

Tasks

- Field data collection - August 15 through December 31/2001

- Writing up observations, interviews, stories

- Sending field data to the Documentarian - September though November/2001

- Sending stories to the Oral historian - September through November/2001

- Data Analysis, issue development - from October through December/2001

- Writing draft of 30 page chapter on the school -November & December/2001

- Submission of an administrative summary of work completed. December 31/2001

- Discussing the drafts with Documentarian, others - December/2001 through January/2002

- Final draft of chapter- January 31/2002

Products from each of three case researchers

- Monthly progress report (1 page) indicating problems encountered, changes in plan;

- Field Notes sent to the Documentarian (electronic files + copy of other documents);

- Stories sent to the Oral Historian (elelctronic files, photocopies of documents)

- Case Study: Rough draft;

- Administrative summary of work completed;

- Case Study: Final draft.

B- Second Focus: Oral Histories from teachers, students, and other persons experienced with EA Program

## Tasks

- Stories collection - from August 15 through December 15/2001

- Observing and writing a two-page mini-report on school visit - September/2001

- Writing up and sending oral histories to Documentarian - September -November/2001

- Analysis of histories from team, issue development - October through December/2001

- Preparing draft of 30 pages chapter on EA Stories-November & December/2001
Submission of an administrative summary of work completed. December 31/2001

- Discussing the draft with Documentarian and others -November & December/2001

- Submission of Final Draft - January 31/2002

Products

- Monthly progress report, indicating problems encountered and changes in plan.

- Field Notes sent to the Documentarian (electronic files + copy of other documents)

- Stories sent to Oral Historian (electronic files, photocopies of documents)

- Mini Case Study: Rough draft

- Administrative summary of work completed

- Draft report on the Analysis of the Oral Histories

- Final Draft of the Oral Histories

C- Third Focus: Discipline-based analysis of EA program.

Tasks

- Conducting and writing a two-page mini-reports on school visits - September/2001

- Reading draft material from the field workers- From October though December/2001

- Reading stories provided by the Oral Historian - From October though December/2001

- Collecting supplementary data on EA program - From October though December/2001

- Writing chapter draft - from December through January/2002

- Submission of an administrative summary of work completed. January 31/2002

- Discussing the drafts with Documentarian and others -January/2000

- Final Draft of chapter - First week of February/2002

Products from each of four topical writers

- Monthly progress report, indicating problems encountered and changes in plan.

- Field notes sent to the Documentarian (electronic files + copy of other documents)

- Chapter Draft report

- Administrative summary of work completed

- Final draft of topical chapter

D. Mini-cases

They are mentioned in the duties and products above.

E. Products from the Director

- Guidelines for selecting schools, collecting and analyzing case study data.

- Monthly status report

- Final Report of the study

Don´t we need task and products related to the Documentarian, Assistant Director and Associated Director? I will try to organize them and then submit to you.

BUDGET

Personnel

Director,       	0.4 time, 8/15-3/15  		        $11,200

Assoc Director	0.5 time, 8/15-3/15	  $10,800

Asst Director 	0.5 time, 8/15-3/15	  $  5,600

Oral Historian	0.5 time, 8/15-12/15	  $  7,200

Documentarian	0.5 time, 9/15-3/15	  $10,800

Fieldworker	0.5 time, 8/15-12/1	  $  6,300

Fieldworker	0.5 time, 8/15-12/1	  $  6,300

Fieldworker	0.5 time, 8/15-12/1	  $  6,300

Topical writer	0.3 time, 9/15-2/1	  $  4,860

Topical writer	0.3 time, 9/15-2/1	  $  4,860

Topical writer	0.3 time, 9/15-2/1	  $  4,860

# Topical writer	0.3 time, 9/15-2/1	  $  4,860

Consultants		  $10,000

$93,940

Travel, lodging and per diem	                                                        $40,000

Office, communications, publication	  $20,000

Direct costs		                                                      $153,940

Indirect costs, host institution	                                                      $  30,788

Total				   $184,728